## Summary
EC-CUBE Manual QA Testing & Bug Reporting — Test Summary
Metrics on this sheet are formulas that read the Execution Data sheet. They are not typed values.
Test Execution Status | Pending
Overall QA Assessment | Pending actual test execution
Release Recommendation | Not assessed
Metric | Value
Total Test Cases | 40
Passed | 0
Failed | 0
Blocked | 0
Not Executed | 40
Not Applicable | 0
Executed Total | 0
Pass Rate | 0%
Total Defects | 0
Critical Defects | 0
High Defects | 0
Medium Defects | 0
Low Defects | 0
Open Defects | 0
Closed Defects | 0

## Execution Data
Execution ID | Test Case ID | Module | Tester | Environment ID | Browser | Operating System | Execution Date | Expected Result | Actual Result | Status | Evidence ID | Defect ID | Retest Required | Notes
EXE-001 | TC-001 | Navigation |  | ENV-EC-001 | Google Chrome | macOS 15.2 |  | The page loads without error. The header, the title "EC-CUBE4.2 デモサイト", four category links, and a hero image area are all visible. | Not Executed | Not Executed | Not Available |  | No
EXE-002 | TC-002 | Navigation |  | ENV-EC-001 | Google Chrome | macOS 15.2 |  | All five controls are visible and correctly labelled. | Not Executed | Not Executed | Not Available |  | No
EXE-003 | TC-003 | Navigation |  | ENV-EC-001 | Google Chrome | macOS 15.2 |  | Four links are shown: 新規カテゴリ, 新入荷, ジェラート, アイスサンド. | Not Executed | Not Executed | Not Available |  | No
EXE-004 | TC-004 | Navigation |  | ENV-EC-001 | Google Chrome | macOS 15.2 |  | The cart badge shows 0 and the total shows ￥0. | Not Executed | Not Executed | Not Available |  | No
EXE-005 | TC-005 | Navigation |  | ENV-EC-001 | Google Chrome | macOS 15.2 |  | A product listing page opens. The breadcrumb shows 全て ¦ ジェラート and a result count in the form 〇件の商品が見つかりました is displayed. | Not Executed | Not Executed | Not Available |  | No
EXE-006 | TC-006 | Navigation |  | ENV-EC-001 | Google Chrome | macOS 15.2 |  | Each link opens a listing page without an error. Each page displays a result count. Counts may differ between categories. | Not Executed | Not Executed | Not Available |  | No
EXE-007 | TC-007 | Navigation |  | ENV-EC-001 | Google Chrome | macOS 15.2 |  | Three indicator dots are shown and exactly one is highlighted as active. | Not Executed | Not Executed | Not Available |  | No
EXE-008 | TC-008 | Product |  | ENV-EC-001 | Google Chrome | macOS 15.2 |  | The stated count equals the number of product tiles displayed. | Not Executed | Not Executed | Not Available |  | No
EXE-009 | TC-009 | Product |  | ENV-EC-001 | Google Chrome | macOS 15.2 |  | Two dropdowns are visible. Observed defaults were 20件 and 価格が低い順. | Not Executed | Not Executed | Not Available |  | No
EXE-010 | TC-010 | Product |  | ENV-EC-001 | Google Chrome | macOS 15.2 |  | The product order changes in a way consistent with the selected sort value. | Not Executed | Not Executed | Not Available |  | No
EXE-011 | TC-011 | Product |  | ENV-EC-001 | Google Chrome | macOS 15.2 |  | The product name is displayed as the page heading and matches the name shown on the listing. | Not Executed | Not Executed | Not Available |  | No
EXE-012 | TC-012 | Product |  | ENV-EC-001 | Google Chrome | macOS 15.2 |  | A main image renders without a broken image placeholder. At least one thumbnail is shown below it. | Not Executed | Not Executed | Not Available |  | No
EXE-013 | TC-013 | Product |  | ENV-EC-001 | Google Chrome | macOS 15.2 |  | The price is shown in yen with a 税込 label. | Not Executed | Not Executed | Not Available |  | No
EXE-014 | TC-014 | Product |  | ENV-EC-001 | Google Chrome | macOS 15.2 |  | Description text is present, readable, and not truncated mid-word or showing placeholder text. | Not Executed | Not Executed | Not Available |  | No
EXE-015 | TC-015 | Product |  | ENV-EC-001 | Google Chrome | macOS 15.2 |  | The related category is displayed as a link. | Not Executed | Not Executed | Not Available |  | No
EXE-016 | TC-016 | Product |  | ENV-EC-001 | Google Chrome | macOS 15.2 |  | A listing page for that category opens and includes the originating product. | Not Executed | Not Executed | Not Available |  | No
EXE-017 | TC-017 | Product |  | ENV-EC-001 | Google Chrome | macOS 15.2 |  | Two option selectors are shown and the price is displayed as a range rather than a single value. | Not Executed | Not Executed | Not Available |  | No
EXE-018 | TC-018 | Cart |  | ENV-EC-001 | Google Chrome | macOS 15.2 |  | A confirmation message reading カートに追加しました。 appears with options to continue shopping or go to the cart. | Not Executed | Not Executed | Not Available |  | No
EXE-019 | TC-019 | Cart |  | ENV-EC-001 | Google Chrome | macOS 15.2 |  | The count increases by one and the total increases by exactly the product price. | Not Executed | Not Executed | Not Available |  | No
EXE-020 | TC-020 | Cart |  | ENV-EC-001 | Google Chrome | macOS 15.2 |  | The product is added and the header cart count increases by one, without needing to open the detail page. | Not Executed | Not Executed | Not Available |  | No
EXE-021 | TC-021 | Cart |  | ENV-EC-001 | Google Chrome | macOS 15.2 |  | The product is not added. A message indicates that options must be selected. The header cart count does not change. | Not Executed | Not Executed | Not Available |  | No
EXE-022 | TC-022 | Cart |  | ENV-EC-001 | Google Chrome | macOS 15.2 |  | The table shows columns 削除, 商品内容, 数量, 小計. The item row displays the correct name, unit price, quantity, and subtotal. | Not Executed | Not Executed | Not Available |  | No
EXE-023 | TC-023 | Cart |  | ENV-EC-001 | Google Chrome | macOS 15.2 |  | Five steps are shown: カートの商品, お客様情報, ご注文手続き, ご注文内容確認, 完了. Step 1 is highlighted as the current step. | Not Executed | Not Executed | Not Available |  | No
EXE-024 | TC-024 | Cart |  | ENV-EC-001 | Google Chrome | macOS 15.2 |  | The quantity increases from 1 to 2. | Not Executed | Not Executed | Not Available |  | No
EXE-025 | TC-025 | Cart |  | ENV-EC-001 | Google Chrome | macOS 15.2 |  | The quantity decreases from 2 to 1. | Not Executed | Not Executed | Not Available |  | No
EXE-026 | TC-026 | Cart |  | ENV-EC-001 | Google Chrome | macOS 15.2 |  | The displayed subtotal equals the manually calculated value. | Not Executed | Not Executed | Not Available |  | No
EXE-027 | TC-027 | Cart |  | ENV-EC-001 | Google Chrome | macOS 15.2 |  | Both figures show the same amount. | Not Executed | Not Executed | Not Available |  | No
EXE-028 | TC-028 | Cart |  | ENV-EC-001 | Google Chrome | macOS 15.2 |  | The cart shows two separate rows, one for each product, each with its own price and quantity. | Not Executed | Not Executed | Not Available |  | No
EXE-029 | TC-029 | Cart |  | ENV-EC-001 | Google Chrome | macOS 15.2 |  | The displayed total equals the manually calculated sum of the line subtotals. | Not Executed | Not Executed | Not Available |  | No
EXE-030 | TC-030 | Cart |  | ENV-EC-001 | Google Chrome | macOS 15.2 |  | The cart line displays the same option values that were selected. | Not Executed | Not Executed | Not Available |  | No
EXE-031 | TC-031 | Cart |  | ENV-EC-001 | Google Chrome | macOS 15.2 |  | The unit price in the cart matches the price shown after the options were selected, and falls within the advertised range. | Not Executed | Not Executed | Not Available |  | No
EXE-032 | TC-032 | Cart |  | ENV-EC-001 | Google Chrome | macOS 15.2 |  | The cart count and total remain unchanged on every page, and the cart page still lists the same items. | Not Executed | Not Executed | Not Available |  | No
EXE-033 | TC-033 | Cart |  | ENV-EC-001 | Google Chrome | macOS 15.2 |  | The same items, quantities, and totals are shown after reload. | Not Executed | Not Executed | Not Available |  | No
EXE-034 | TC-034 | Registration |  | ENV-EC-001 | Google Chrome | macOS 15.2 |  | The form shows お名前, お名前(カナ), 会社名, 住所 with postal code and prefecture controls, 電話番号, メールアドレス, パスワード, 生年月日, 性別, 職業, and メールマガジン送付について. Required fields carry a 必須 marker. | Not Executed | Not Executed | Not Available |  | No
EXE-035 | TC-035 | Registration |  | ENV-EC-001 | Google Chrome | macOS 15.2 |  | The form is not submitted. Each required field is highlighted and displays 入力されていません。 The user remains on the registration page. | Not Executed | Not Executed | Not Available |  | No
EXE-036 | TC-036 | Registration |  | ENV-EC-001 | Google Chrome | macOS 15.2 |  | Fields without a 必須 marker show no validation error. | Not Executed | Not Executed | Not Available |  | No
EXE-037 | TC-037 | Registration |  | ENV-EC-001 | Google Chrome | macOS 15.2 |  | A validation message appears indicating the katakana fields require katakana characters. The form is not submitted. | Not Executed | Not Executed | Not Available |  | No
EXE-038 | TC-038 | Registration |  | ENV-EC-001 | Google Chrome | macOS 15.2 |  | An external postal code search page opens in a new browser tab, and the registration page remains open in the original tab. | Not Executed | Not Executed | Not Available |  | No
EXE-039 | TC-039 | Account |  | ENV-EC-001 | Google Chrome | macOS 15.2 |  | All four elements render on the login page. | Not Executed | Not Executed | Not Available |  | No
EXE-040 | TC-040 | System |  | ENV-EC-001 | Google Chrome | macOS 15.2 |  | A page displays ページがみつかりません。 with the guidance URLに間違いがないかご確認ください。 and a トップページへ button that returns to the home page. | Not Executed | Not Executed | Not Available |  | No

## Defect Data
Bug ID | Title | Module | Environment | Preconditions | Steps to Reproduce | Test Data | Expected Result | Actual Result | Reproducibility | Severity | Priority | Status | Evidence | Related Test Case | Reported Date | Retest Result | Notes | Empty by design. Add a row only after a defect has been reproduced at least twice.